## 2-Month Sprint Plan (3-Person)
2-MONTH PRODUCTION DELIVERY PLAN (1 FE + 1 BE + 1 QA — 8 WEEKS / 40 WORKING DAYS)
Role / Engineer | Capacity (8 Wks) | Sprint 1 (W1-2) | Sprint 2 (W3-4) | Sprint 3 (W5-6) | Sprint 4 (W7-8) | Total Allocated
1x Frontend Engineer | 40 Mandays | 10 MD | 10 MD | 10 MD | 10 MD | 40 MD (100% capacity)
1x Backend Engineer | 40 Mandays | 10 MD | 10 MD | 10 MD | 10 MD | 40 MD (100% capacity)
1x QA / Automation Engineer | 40 Mandays | 10 MD | 10 MD | 10 MD | 10 MD | 40 MD (100% capacity)
TOTAL SPRINT EFFORT | 120 Mandays | 30 Mandays | 30 Mandays | 30 Mandays | 30 Mandays | 120 MD / 8 Weeks
Sprint # | Timeline | Frontend Milestone | Backend Milestone | QA Milestone | Sprint Release Goal
Sprint 1 | Weeks 1–2 | UI Shell, Multi-Role Login, Academic & Question Bank Authoring UI | DB Schemas, JWT Auth/RBAC, Academic APIs & Question Bank Storage | Auth & Academic CRUD automated test suites | Working Foundation + Question Repository
Sprint 2 | Weeks 3–4 | 7-Step Exam Creation Wizard (Pool + PDF Upload), Live Classroom UI | Exam Engine & Scheduling APIs, PDF Upload S3 Service, WebSockets | Exam wizard validation & Live class latency testing | Functional Exam Creator & Live Class Gateway
Sprint 3 | Weeks 5–6 | Pre-Exam System Check, Secure Lockdown Workspace, Proctoring Grid | Session Init, Resilient Auto-Save Pipeline, Telemetry & Risk Scoring Bus | Exam resilience, auto-save dropout stress test & anti-cheat | Full Student Exam Experience & Live Proctoring
Sprint 4 | Weeks 7–8 | Evaluation Dashboard, PDF Pen Grading Tool, 4-Tier Approval & Scorecards | Auto-grading, Manual rubric APIs, 4-Tier Approval State Machine, Reports | Full regression, Security audit, UAT Sign-Off | Production Launch & Go-Live

## Sprint Tasks Breakdown
Task ID | Sprint | Week | Phase | Track | Module | Task Name | Description | Assigned To | Complexity | Mandays | Key Deliverable / Artifact
FE-101 | Sprint 1 (W1-2) | Week 1 | Phase 1: Foundation & RBAC | Frontend | UI Framework | Design System, Shell Layout & Dynamic Role Switcher | Responsive layout, Sidebar, Header, Role Switcher (Admin/Coord/Teacher/Proctor/Student/Parent), core UI components | 1x Frontend Engineer | Medium | 3 | Global Layout, Role Switcher & Atomic UI Kit
BE-101 | Sprint 1 (W1-2) | Week 1 | Phase 1: Foundation & RBAC | Backend | Database & Architecture | PostgreSQL Schema, Models & Migration Pipeline | Database schema for Tenants, Academic Hierarchy, Users, Roles, Permissions, Accommodations, indexing and constraints | 1x Backend Engineer | High | 3 | PostgreSQL Schema & Prisma/ORM Models
FE-102 | Sprint 1 (W1-2) | Week 1 | Phase 1: Foundation & RBAC | Frontend | Authentication | Multi-Role Login & ERP Seamless SSO Portal | Email/Password & Student PIN login forms, Seamless ERP 1-Click SSO Launch receiver (JWT/LTI 1.3), role route guards, auto-refresh tokens | 1x Frontend Engineer | Medium | 2 | Login Views, ERP SSO Receiver, Role Guards
BE-102 | Sprint 1 (W1-2) | Week 1 | Phase 1: Foundation & RBAC | Backend | Authentication | JWT Auth, ERP SSO Handshake & JIT Provisioning | Endpoints for native login, ERP Signed Launch Token validator, Just-In-Time (JIT) student/staff auto-provisioning, and RBAC middleware | 1x Backend Engineer | High | 3 | Auth REST APIs, ERP SSO Handshake & JIT Provisioner
QA-101 | Sprint 1 (W1-2) | Week 1-2 | Phase 1 & 2 QA | QA & Testing | Test Architecture | Test Environment Setup & Auth/Academic Test Cases | Setup automated test framework (Playwright/Postman), write test suites for Auth, RBAC permissions, and Academic CRUD APIs | 1x QA Engineer | Medium | 10 | Automated Test Suite for Auth & Core APIs
FE-103 | Sprint 1 (W1-2) | Week 2 | Phase 1: Foundation & RBAC | Frontend | Academic Master Data | Academic Hierarchy & User Roster Management UI | CRUD screens for Academic Years, Classes, Divisions, Subjects, Chapters, and Student roster with Accommodations modal | 1x Frontend Engineer | Medium | 2 | Academic Structure & User Views
BE-103 | Sprint 1 (W1-2) | Week 2 | Phase 1: Foundation & RBAC | Backend | Academic Services | Academic Hierarchy & Roster CRUD APIs | REST endpoints for Academic structure, Teacher allocations, Student roster, Accommodations, and CSV bulk import | 1x Backend Engineer | Medium | 2 | Academic & User CRUD REST APIs
FE-201 | Sprint 1 (W1-2) | Week 2 | Phase 2: Question Bank | Frontend | Question Bank | Question Bank Explorer & Multi-Type Authoring UI | Question explorer with hierarchy filter, authoring for MCQ, One-word, Short/Long, Essay with KaTeX formulas and rubrics | 1x Frontend Engineer | High | 3 | Question Bank Explorer & Authoring Studio
BE-201 | Sprint 1 (W1-2) | Week 2 | Phase 2: Question Bank | Backend | Question Bank | Question Bank Storage, Search & Randomizer APIs | Question schemas, full-text search, subject/chapter filtering, bulk CSV question import, and dynamic random question pool selector | 1x Backend Engineer | High | 2 | Question Bank API Suite & Randomizer
FE-301 | Sprint 2 (W3-4) | Week 3-4 | Phase 3: Exam Wizard | Frontend | Exam Creation | 7-Step Exam Creation Wizard (Pool + PDF Upload) | Step 1 (Basic info), Step 2 (Recipients), Step 3 (Academic mapping), Step 4 (Source), Step 5 (Marks matrix & PDF setup), Step 6 (Controls), Step 7 (Publish) | 1x Frontend Engineer | High | 6 | Complete 7-Step Exam Creation Wizard
BE-301 | Sprint 2 (W3-4) | Week 3 | Phase 3: Exam Wizard | Backend | Exam Engine | Exam Engine Schemas, CRUD & Multi-Step APIs | Exams, Recipients, Questions, Sections, Security models, validation pipeline, and state machine (Draft -> Scheduled -> Active) | 1x Backend Engineer | High | 4 | Exam Configuration & Scheduler APIs
BE-302 | Sprint 2 (W3-4) | Week 4 | Phase 3: Exam Wizard | Backend | PDF Paper Engine | PDF Question Paper Upload & Section Setup Service | Multipart PDF upload to S3/GCS, section schema storage (Section A/B/C, max marks, choice rules), and PDF URL signing | 1x Backend Engineer | Medium | 2 | PDF Upload & Section Setup APIs
FE-401 | Sprint 2 (W3-4) | Week 4 | Phase 4: Live Classes | Frontend | Virtual Classroom | Live Classroom UI & Spot Quiz Real-Time Modal | Teacher video grid/Meet embed, attendance list, 1-click spot quiz trigger, live response bar chart, student quiz popup | 1x Frontend Engineer | High | 4 | Live Classroom & Spot Quiz Overlay UI
BE-401 | Sprint 2 (W3-4) | Week 4 | Phase 4: Live Classes | Backend | WebSockets | Live Class Signaling & Spot Quiz Redis Collector | WebSocket gateway for classroom events (join/leave/chat), attendance heartbeat tracker, and sub-second in-memory spot quiz collector | 1x Backend Engineer | High | 4 | Classroom WebSocket Gateway & Spot Quiz Engine
QA-102 | Sprint 2 (W3-4) | Week 3-4 | Phase 3 & 4 QA | QA & Testing | Exam & Class Testing | Exam Creation Flow, PDF Parsing & Live WS Testing | Validate 7-step wizard validations, marks matching, PDF uploads, recipient assignments, WebRTC signaling & spot quiz broadcast latency | 1x QA Engineer | High | 10 | Exam Wizard & Live Class QA Verification Report
FE-501 | Sprint 3 (W5-6) | Week 5 | Phase 5: Student Exam | Frontend | Pre-Exam Check | Student Pre-Exam System Readiness Check Wizard | 4-Step Pre-check: Cam & Mic check, AI Face identification, Network ping/bandwidth test, Fullscreen & exam rules acknowledgement | 1x Frontend Engineer | High | 3 | System Readiness Check Wizard View
BE-501 | Sprint 3 (W5-6) | Week 5 | Phase 5: Student Exam | Backend | Session Security | Student Session Init & Encrypted Token Generator | Time window & eligibility verification, device readiness logging, reference selfie storage, and tamper-proof session token generator | 1x Backend Engineer | Medium | 2 | Student Session Init & Token Service
FE-502 | Sprint 3 (W5-6) | Week 5-6 | Phase 5: Student Exam | Frontend | Exam Interface | Secure Exam Lockdown Workspace & Palette | Locked-down Fullscreen UI, Tab switch detector, accommodations countdown timer, Question Palette (Answered/Review/Unanswered), auto-save sync | 1x Frontend Engineer | High | 4 | Locked-Down Exam Interface & Question Palette
BE-502 | Sprint 3 (W5-6) | Week 5-6 | Phase 5: Student Exam | Backend | Auto-Save Engine | Resilient Auto-Save Pipeline & Auto-Submit Daemon | Redis keystroke buffer, batch flush to Postgres every 10s, S3 attachment uploads, server-side timer daemon to auto-close expired exams | 1x Backend Engineer | High | 4 | Fault-Tolerant Auto-Save & Auto-Close Daemon
FE-601 | Sprint 3 (W5-6) | Week 6 | Phase 6: Proctoring | Frontend | Live Proctoring | Invigilator Live Monitoring Grid & Alert Drawer | Tile grid of student webcams, risk score color badges (0-100), quick actions (warn, pause, terminate), malpractice violation timeline | 1x Frontend Engineer | High | 3 | Invigilator Monitoring Grid & Alerts UI
BE-601 | Sprint 3 (W5-6) | Week 6 | Phase 6: Proctoring | Backend | Proctoring Bus | Telemetry Ingestion Bus & Dynamic Risk Scoring Engine | WebSockets (/proctor-feed), telemetry event parser (tab switch, face lost, multi-face), 0-100 risk scoring algorithm, S3 snapshot vault | 1x Backend Engineer | High | 4 | Real-time Telemetry & Risk Scoring Service
QA-103 | Sprint 3 (W5-6) | Week 5-6 | Phase 5 & 6 QA | QA & Testing | Security & Exam Testing | Exam Lockdown, Auto-Save Stress Test & Proctoring Simulation | Simulate network dropouts during exam, verify offline answer recovery, test tab-switch traps, simulate 50+ proctor telemetry events simultaneously | 1x QA Engineer | High | 10 | Resilience & Security Test Sign-off Report
FE-701 | Sprint 4 (W7-8) | Week 7 | Phase 7: Evaluation | Frontend | Grading Workspace | Teacher Evaluation Dashboard & PDF Annotation Canvas | Submission queue, blind grading mode (mask PII), side-by-side rubric grading, and interactive PDF digital pen annotation tool | 1x Frontend Engineer | High | 4 | Evaluation Dashboard & PDF Grading Canvas
BE-701 | Sprint 4 (W7-8) | Week 7 | Phase 7: Evaluation | Backend | Auto & Manual Grading | Auto-Grading Worker & Vector Annotation Storage APIs | Auto-eval worker for MCQ & One-Word, manual rubric grading APIs, blind evaluation PII masking, vector JSON pen annotation storage | 1x Backend Engineer | High | 4 | Auto-Grading & Manual Evaluation APIs
FE-702 | Sprint 4 (W7-8) | Week 7-8 | Phase 7: Result Approval | Frontend | Approval Workflow | 4-Tier Result Approval & Moderation UI | Progress steps (Eval Done -> Teacher Review -> Coordinator Sign-Off -> Published), Grace marks / formula runner, Official Publish action | 1x Frontend Engineer | Medium | 2 | 4-Tier Result Approval & Moderation Views
BE-702 | Sprint 4 (W7-8) | Week 7-8 | Phase 7: Result Approval | Backend | Approval Engine | 4-Tier Approval State Machine & Moderation Processor | State machine transitions, grace mark processor, grade computation, coordinator signature verification, and immutable sign-off logs | 1x Backend Engineer | High | 3 | Result Approval State Machine Engine
FE-801 | Sprint 4 (W7-8) | Week 8 | Phase 8: Reports & Portals | Frontend | Scorecards & Reports | Student/Parent Scorecards & ERP Sync Status Dashboard | Student/Parent report cards, topic mastery radar charts, question review modal, and ERP Gradebook Sync Status view with manual retry triggers | 1x Frontend Engineer | Medium | 4 | Scorecard Portals & ERP Sync Status Dashboard
BE-801 | Sprint 4 (W7-8) | Week 8 | Phase 8: Reports & Portals | Backend | Reports & ERP | Batch PDF Generator, ERP Gradebook Sync & LTI 1.3 AGS | PDF report card generator (Puppeteer/PDFKit), multi-channel notification dispatcher, Bi-directional School ERP Sync webhook adapter, and LTI 1.3 Assignment & Grade Service stub | 1x Backend Engineer | High | 3 | PDF Generator, ERP Sync Adapter & LTI 1.3 AGS
QA-104 | Sprint 4 (W7-8) | Week 7-8 | Phase 7 & 8 QA | QA & Testing | Regression & Launch | Full End-to-End Regression, Security Pentest & UAT Sign-Off | Full end-to-end regression of entire exam cycle, OWASP security checks, load testing evaluation submission spikes, and User Acceptance Testing sign-off | 1x QA Engineer | High | 10 | Final QA Production Release Sign-Off